## Sheet1
Topic | Task |  | February |  |  |  | March |  |  |  | April
|  | Week -> | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Yoga Expert Interview | Gather ideal yoga poses | bar: February 3
Identify currect error detection methods | bar: February 3
Pose Teaching | Pose Detection | bar: February 3 to February 4
Pose Comparison | bar: February 4 to February 6
Error Identification | bar: February 4 to February 6
Hardware Construction | Material Acquisition | bar: February 4
Woodworking | bar: February 5 to February 6
Physical Contstruction | bar: February 5 to February 6
Camera Integration | bar: March 9
Mirror-Camera Coordination | Camera Callibration | bar: March 10 to April 11
Coordinate Mapping | bar: March 10 to April 11
Mirror UI | Error Display | bar: March 9 to April 11
Magic Mirror Library Integration | bar: March 10
Audio Feedback on error | bar: April 12
Testing & Validation | Pose Accuracy testing | bar: March 9; April 12
Latency testing | bar: April 13
User Testing | bar: April 13
Slack & Bonus | Yoga Mat usage | bar: March 7; April 14
Adding user profile | bar: March 7; April 14
Hand gesture interaction | bar: March 7; April 14